## Slide 1: Section 2

## Slide 2: Section Two Management : Topics

## Slide 3: Chapter 7 Management models and the business case
A model, processes, system or a Body of Knowledge
  Qualities of a good model
The event management environment: Complexity and Uncertainty
Olympic Torch,
Photo courtesy of Maxxam Events International

## Slide 4: Chapter 7 Management models and the business case
Complexity due to:
  Number of stakeholders
  Number of reciprocal dependencies
  Multi-objectives
  Number of changes or modifications to both the product and the project
  Uncertainty of goals
  Uncertainty of methods

## Slide 5: Chapter 7 Management models and the business case
Dynamic System
  Dynamic – change on many levels
  Tightly coupled – changes in one area of the management will quickly affect other areas
  Governed by feedback – any action will have a result that will influence other similar actions
  Nonlinear – effect and cause are rarely proportional
  History dependent – actions are mostly irreversible
  Self-organising – semi-autonomous groups or teams
  Adaptive – can quickly respond to changes to minimise their negative impact
  Counterintuitive – difficult to exactly predict
  Policy resistive – difficult to comprehend and therefore control using linear methods
  Characterised by trade-offs – the effects of a decision in one area of event management will be traded against the results in other areas

## Slide 6: Chapter 7 Management models and the business case
Phases of event management and the event life cycle
  Idea – concept development
  Feasibility
  Planning
  Implementation
  Setup
  Event
  Shutdown
Intangibility of outcomes
  ROI
  ROO
  ROE
Photo courtesy of Maxxam Events International

## Slide 7: Chapter 7 Management models and the business case
The Business case
  The business case is the justification to proceed with an event from a business point of view.
A template for a business case will include the headings:
  Date: Event:
  Purpose:
  Event Description
  Target Audience
  Company Participation & Staffing
  Required resources
  Costs
  Company benefits: Direct
  Company benefits: Indirect
  Action recommended

## Slide 8: Chapter 8 Setting up the management system
Event project methodology
Management framework during the feasibility/initiation phase
  Scoping
  Drafting

## Slide 9: Chapter 8 Setting up the management system
Management framework as a spreadsheet
  Contents page
    Link to all spreadsheets
  The scope
    The objectives of the event as well as the major responsibilities and assumptions
  The organisation structure
    Temporary organisation structure that is time based

## Slide 10: Chapter 8 Setting up the management system
Management framework as a spreadsheet
  The Stakeholder List
    identification, engagement, requirement analysis, planning, implementation, control and evaluation
  Work Breakdown Structure
    a process of decomposition whereby a complex project is broken up into smaller units of work that can be easily managed
  The Schedule: Milestones
    dates that mark the conclusion of an important task
    Deliverables
    Each milestone and its deliverable is a mini project

## Slide 11: Chapter 8 Setting up the management system
Management framework as a spreadsheet
  The Resources
    outsource /inhouse and make/buy/hire decisions
  The budget
  The programme
  The risk register
  The site map
  The event checklist
Photo courtesy of Peter Kagwa, Eventswarehouse, Uganda

## Slide 12: Chapter 8 Setting up the management system
The developing event: a maturity model
How events start and their pathway to growth
  Informal
  Formal
  Accountable
  Adaptable and improvable

## Slide 13: Chapter 9 Event management processes
From domains to a process model
  1. Domain
  2. Phase
  3. Processes that are employed
  A process is series of step by step tasks or activities repeated in the management of an event
  Process groups
    Scope: the integration and control of all the work flows
    Stakeholders including sponsorship management
    Design
    Marketing
    Finance
    Time
    Risk
    Communication
    Procurement
    Human Resources

## Slide 15: Chapter 9 Event management processes
Process groups
  Scope: the integration and control of all the work flows

## Slide 16: Chapter 9 Event management processes
Process groups
  Stakeholders including sponsorship management

## Slide 17: Chapter 9 Event management processes
Process groups
  Design
    Event site
    Programme
  Marketing
    Marketing mix
    Promotion

## Slide 18: Chapter 9 Event management processes
Process groups
  Finance
    Budget
    Pricing
    Cost
    Cash flow
    Pricing event
    management services

## Slide 19: Chapter 10 Event management processes – section two
Time management process
    Event Date
    Deadline Management

## Slide 20: The deadline
The immoveable deadline is one of the defining characteristic of most events
Every decision and change must take into account the effect on the deadline
The deadline analysis flowchart is a universal process in the event management model

## Slide 21: Chapter 10 Event management processes – section two
Risk Management Process
    Operational Risk and Upstream Design
Queen’s Baton Relay 2010, Namibia,
Photo courtesy of Maxxam Events International

## Slide 22: Chapter 10 Event management processes – section two
Communication process
    External Communication – Promotion
    Internal Staff
      Documentation/Office
      Administration Manual
      IT system
      Internal Volunteers
      Meetings, briefings
    Internal – during event :
      Onsite Communication systems
      Operation manual
    External – stakeholders:
      Progress Reporting such as legal requirements
      Promoting (audience)
      Development (sponsors)

## Slide 23: Chapter 10 Event management processes – section two
Procurement Process
    Contract management
Human Resources Process
    HR and Delegation

## Slide 24: Chapter 11 Event metrics and checklists
Metrics
  Exposure Profile
Return on Investment
  (Income − Cost)/Cost
  Compare investments – a commensurable variable
  Return on Objectives (ROO)
  The general process of ROI analysis is:
    Establish the client of the ROI
    Establish objective of the client
    Create a system for correctly costing the event
    Analyse the elements of the event that directly contribute to the income
    Analysis of the elements that indirectly contribute to the income
    Develop a measure for the intangible aspects
    Establish the time frame of the incoming
    Analyse the efficiency of the elements of the event to deliver the incoming